## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Input target (domain/IP) for analysis | MUST HAVE | None | Kallem Architha Reddy | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Detect target type automatically | MUST HAVE | Input module | Kallem Architha Reddy | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Run Nmap scan for exposure detection | MUST HAVE | Nmap | Kallem Architha Reddy | 3- Completed
Sprint 2 | Sprint 2 | US-4 | Fetch VirusTotal data | MUST HAVE | API key | Kallem Architha Reddy | 3- Completed
Sprint 2 | Sprint 2 | US-5 | Support URL and file hash analysis | SHOULD HAVE | VT API | Kallem Architha Reddy | 3- Completed
Sprint 2 | Sprint 2 | US-6 | Integrate WHOIS lookup | COULD HAVE | WHOIS lib | Kallem Architha Reddy | 3- Completed
Sprint 3 | Sprint 3 | US-7 | Process raw scan data into structured format | MUST HAVE | Scanner | Kallem Architha Reddy | 3- Completed
Sprint 3 | Sprint 3 | US-8 | Calculate exposure, threat, context scores | MUST HAVE | Processor | Kallem Architha Reddy | 3- Completed
Sprint 3 | Sprint 3 | US-9 | Generate overall risk score | MUST HAVE | Scoring | Kallem Architha Reddy | 3- Completed
Sprint 4 | Sprint 4 | US-10 | Display summary dashboard | MUST HAVE | Backend | Kallem Architha Reddy | 3- Completed
Sprint 4 | Sprint 4 | US-11 | Add charts and visualizations | MUST HAVE | Plotly | Kallem Architha Reddy | 3- Completed
Sprint 4 | Sprint 4 | US-12 | Create multi-page UI | MUST HAVE | UI | Kallem Architha Reddy | 3- Completed
Sprint 5 | Sprint 5 | US-13 | Store scan history in database | MUST HAVE | SQLite | Kallem Architha Reddy | 3- Completed
Sprint 5 | Sprint 5 | US-14 | Compare previous scans | SHOULD HAVE | DB | Kallem Architha Reddy | 3- Completed
Sprint 5 | Sprint 5 | US-15 | Send email alerts | MUST HAVE | Email service | Kallem Architha Reddy | 3- Completed
print 6 | Sprint 6 | US-16 | Add SSL validation | COULD HAVE | SSL logic | Kallem Architha Reddy | 3- Completed
Sprint 6 | Sprint 6 | US-17 | Add recommendations engine | SHOULD HAVE | Scoring | Kallem Architha Reddy | 3- Completed
Sprint 6 | Sprint 6 | US-18 | Improve UI/UX | SHOULD HAVE | UI | Kallem Architha Reddy | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7